## Route Plan
Preferred Roll-out plan
Note: Plan is subject to change depending on conditions, security, and final agreement with the contracted agency.
A contracted agency will be responsible for on-ground implementation and reporting, with USAID-PEP managing all aspects of design, and project management - including reporting templates.
No. | Activation Locations | District | Province | Activation Sector | Region | Activation Line-up (Chronology) | Awareness + Travel Days | No. of Activations/Day | Activation Sites | Total Activations/Sector | Travel | Accommodation | Comments | Advertising Schedule
1 | Voco Point Wharf | Lae | Morobe | Lae Urban | Momase | 1 | 1 | 3 | Voco Point DCA Aigris | 3 | *start in Lae |  | *road activation at Zenag Farm | t-7 days
2 | Top Town CBD | Lae | Morobe |  |  |  | 1 | 3 | Top Town Eriku Kamkumung | 3
3 | Lae Main Market | Lae | Morobe |  |  |  | 1 | 3 | Main Market China Town Malahang | 3
[7 empty] | 1 |  |  | 1 | *travel Lae-Bulolo | *camp at Bulolo | *road activation at Zenag Farm
4 | Bulolo Township Market | Bulolo | Morobe | Bulolo-Wau |  | 2 | 1 | 1 |  | 1 |  |  |  | t-7 days
5 | Wau Station | Wau-Waria | Morobe |  |  |  | 1 | 1 |  | 1 |  |  | *activate at Wau | t-7 days
[7 empty] | 1 |  |  |  | *travel Wau-Lae | *camp at Lae
[7 empty] | 1 | [5 empty] | *rest & reset
6 | Nadzab Market | Huon Gulf | Morobe | Huon-Markham |  | 3 | 1 | 2 | Nadzab 40 mile | 2 |  |  |  | t-7 days
7 | Markham Valley-Mutzing Market | Markham | Morobe |  |  |  | 1 | 2 | Mutzing Umi | 2 | *travel Lae-Gusap | *camp at Gusap | *activate and travel
1
8 | Gusap (Ramu) Station Market | Markham | Morobe | Watarais-Usino |  | 4 | 1 | 1 |  | 1 |  |  |  | t-7 days
9 | Walium Station Market | Usino Bundi | Madang |  |  |  | 1 | 1 |  | 1 | *travel Gusap-Madang | *camp at Madang | *activate and travel
10 | Madang Main Market/CBD | Madang | Madang | Madang |  | 5 | 1 | 3 | Main Market Boat stop Paramed/Uni | 3 |  |  |  | t-7 days
[7 empty] | 1 | [5 empty] | *rest & reset
*begin Momase return leg
11 | Madang Main Market/CBD | Madang | Madang | Madang |  | 6 | 1 | 3 | Main Market Boat stop Paramed/Uni | 3
12 | Walium Station Market | Usino Bundi | Madang | Watarais-Usino |  | 7 | 1 | 1 |  | 1 | *travel Madang-Gusap | *camp at Gusap | *activate and travel
13 | Gusap (Ramu) Station Market | Markham | Morobe |  |  |  | 1 | 1 |  | 1
14 | Markham Valley-Mutzing Market | Markham | Morobe | Huon-Markham |  | 8 | 1 | 1 | Mutzing Market Nadzab | 2 | *travel Gusap-Lae | *camp at Lae | *activate and travel
15 | Lae Main Market | Lae | Morobe | Lae Urban |  | 9 | 1 | 3 | Main Market China Town Malahang | 3 |  |  |  | t-7 days
16 | Top Town CBD | Lae | Morobe |  |  |  | 1 | 3 | Top Town Eriku Kamkumung | 3
17 | Voco Point Wharf | Lae | Morobe |  |  |  | 1 | 3 | Voco Point DCA Aigris | 3
Rest-Recover-Reset-Restart in Lae | [6 empty] | 3 | [5 empty] | *rest, restock, re-strategize etc..
18 | Yonki Market | Obura-Wonenara | EHP | Yonki-Henganofi |  | 10 | 1 | 1 | Yonki Market | 1 | *travel Lae-Kainantu | *camp at Kainantu | *activate and travel | t-7 days
19 | Kainantu Market | Kainantu | EHP |  | Highlands |  | 2 | 1 | Kainantu CBD Henganofi | 2 |  |  | *Day 1 - Kainantu *Day 2 - Activate & travel
[12 empty] | *camp at Goroka |  | t-7 days
20 | Goroka Town CBD | Goroka | EHP | Goroka Urban |  | 11 | 2 | 3 | Goroka CBD Main Market West Faniufa Asaro Station Uni gate | 6
21 | Chuave Market (Gate) | Chuave | Simbu | Chuave-Kumbal |  | 12 | 1 | 1 |  | 1 | *travel Goroka-Kundiawa | *camp at Kundiawa | *activate and travel
22 | Kundiawa Town CBD | Simbu Urban | Simbu |  |  |  | 2 | 2 | Kuniawa CBD Wara Market Mingende Kumbal | 4 | *travel Kundiawa-Banz (Day 2) |  | *Day 1 - Kundiawa CBD & Wara Market *Day 2 - Activate & travel | t-7 days
[7 empty] | 1 | [5 empty] | *rest & reset
23 | Banz Town | North Waghi | Jiwaka | Minj-Kindeng |  | 13 | 2 | 2 | Banz CBD Kudjip Minj Kindeng | 4 | *travel Banz-Hagen (Day 2) | *camp at Banz | *Day 1 - Banz & Kudjip *Day 2 - Activate & travel | t-7 days
24 | Hagen Town CBD | Mt Hagen | WHP | Hagen Urban |  | 14 | 2 | 4 | Hagen CBD Top Town Market Oka Pana Market Airport Market Main Market Main Bus stop Tininga Central Tininga Dobel | 8 |  | *camp at Hagen |  | t-7 days
*maintain camp
25 | Walume Junction | Imbonggu | SHP | SHP |  | 15 | 1 | 2 | Walume Ialibu | 2 |  |  | *travel, activate, rtn to Hagen | t-7 days
[7 empty] | 1 | [5 empty] | *rest & reset
*begin Highlands return leg
26 | Hagen Town CBD | Mt Hagen | WHP | Hagen Urban |  | 16 | 1 | 4 | Hagen CBD Top Town Market Oka Pana Market Main Bus stop | 4
27 | Banz Market | North Waghi | Jiwaka | Kindeng-Mingende |  | 17 | 1 | 2 | Kudjip Banz CBD | 2 | *travel Hagen-Banz | *camp at Banz | *activate and travel | t-7 days
28 | Minj | South Waghi | Jiwaka |  |  |  | 1 | 3 | Minj Kumbal Mingende | 2 | *travel Banz-Kundiawa | *camp at Kundiawa | *road activations at Minj, Kumbal & Mingende | t-7 days
29 | Kundiawa Town CBD | Simbu Urban | Simbu | Kundiawa-Chuave |  | 18 | 1 | 2 | Kundiawa CBD Wara Market | 2
30 | Chuave Market (Gate) | Chuave | Simbu |  |  |  | 1 | 1 |  | 1 | *travel Kundiawa-Goroka | *camp at Goroka | *activate and travel
31 | Goroka Town CBD | Goroka | EHP | Goroka Urban |  | 19 | 1 | 3 | Goroka CBD Main Market West | 3 |  |  |  | t-7 days
32 | Kainantu Market | Kainantu | EHP | Henganofi-Yonki |  | 20 | 3 | 1 | Henganofi Kainantu CBD Yonki Market | 3 | *travel Goroka-Kainantu *travel Kainantu-Lae | *camp at Kainantu | *Day 1 - activate Henganofi, travel Kainantu *Day 2 - activate Kainantu *Day 3 - activate Yonki, travel Lae | t-7 days
[6 empty] | Totals | 49 |  |  | 82
[6 empty] | Training | 3 days
[6 empty] | Contingency | 3 Days |  |  | 5
[7 empty] | 55 |  |  | 87
Note on H61: 2 days prior to launch, 1 days prior to start of second leg

## Collateral Examples
Trifold Brochure
Tent, tear drop stand, t-shirt